## RMWL
Task Name | Duration | Start | Finish | Predecessors | Resource Names | Assist By
Apex Migration | 14.88 days | Thu 5/14/20 | Tue 6/9/20
Setting Up The System
Transaction Type setup | 1 day | Thu 5/14/20 | Thu 5/14/20 |  | Monir Hossain
Model Rate Modification | 2 days | Sun 5/17/20 | Tue 5/19/20 | 2 | Monir Hossain
Item Master (Tebular) | 1 day | Thu 5/14/20 | Thu 5/14/20 |  | Julhas Razu
Service Job Type | 2 days | Wed 5/20/20 | Thu 5/21/20 | 3 | Monir Hossain
Grade Wise Discount | 1 day | Thu 5/14/20 | Thu 5/14/20 |  | Mukul Ahmed
Vat Rule Setup | 4 hrs | Sun 5/17/20 | Sun 5/17/20 | 6 | Mukul Ahmed
Code Parameter | 4 hrs | Thu 5/14/20 | Thu 5/14/20 |  | Nadia Rashid
Item Master | 4 hrs | Sun 5/17/20 | Sun 5/17/20 |  | Nadia Rashid
service Engineer Master | 1 day | Sun 5/17/20 | Mon 5/18/20 | 4 | Julhas Razu
Warehouse Master | 1 day | Thu 5/14/20 | Thu 5/14/20
Cost Center Master | 4 hrs | Sun 5/17/20 | Mon 5/18/20 | 7 | Mukul Ahmed
Unit of Masurement (UOM) Master | 4 hrs | Sun 5/17/20 | Mon 5/18/20 | 9 | Nadia Rashid
Salesman Master | 1 day | Mon 5/18/20 | Tue 5/19/20 | 10 | Julhas Razu
Service Charge Master | 1 day | Tue 5/19/20 | Wed 5/20/20 | 14 | Julhas Razu
Service Package Setup | 1 day | Thu 5/28/20 | Thu 5/28/20 |  | Monir Hossain
Service Type Master | 1 day | Mon 5/18/20 | Tue 5/19/20 | 12 | Mukul Ahmed
Accounts Group Master | 1 day | Tue 5/19/20 | Tue 5/19/20 |  | Nadia Rashid
Discount Rule Setup | 4 hrs | Wed 5/20/20 | Wed 5/20/20 | 18 | Nadia Rashid
Party Master | 1.63 days | Sun 5/31/20 | Mon 6/1/20 | 16 | Monir Hossain
Currency Master | 4 hrs | Tue 5/19/20 | Tue 5/19/20 | 17 | Mukul Ahmed
Company Parameter Setup | 6 hrs | Wed 5/20/20 | Thu 5/21/20 | 19 | Nadia Rashid
Document Parameter Setup | 4 hrs | Thu 5/21/20 | Thu 5/21/20 | 22 | Nadia Rashid
Workflow Definition | 1 day | Wed 5/20/20 | Thu 5/21/20 | 15 | Julhas Razu
System Control
Program master | 4 hrs | Thu 5/21/20 | Thu 5/21/20 | 24 | Julhas Razu
Menu master | 1 day | Thu 5/21/20 | Wed 5/27/20 | 26 | Mukul Ahmed
Cost Center Access | 1 day | Tue 6/2/20 | Tue 6/2/20 | 20 | Monir Hossain
User Master | 1 day | Wed 5/27/20 | Wed 5/27/20 | 23 | Nadia Rashid
User Rights Master | 1 day | Wed 6/3/20 | Wed 6/3/20 | 28 | Monir Hossain
Application Session Control | 1 day | Thu 5/14/20 | Thu 5/14/20 |  | Mukul Ahmed
Use Signup | 1 day? | Sun 5/17/20 | Mon 5/18/20 | 31
Admin Message | 1 day | Wed 5/27/20 | Thu 5/28/20 | 27 | Mukul Ahmed
Sub Cost Center | 1 day | Thu 6/4/20 | Thu 6/4/20 | 29 | Nadia Rashid
Bill Party | 2 days | Thu 5/21/20 | Thu 5/28/20 | 26 | Julhas Razu
Procurement Management
Lost Register Entry | 1.5 days | Mon 6/1/20 | Tue 6/2/20 | 33 | Mukul Ahmed | Masum Miah
Forcasting | 2.2 days | Mon 6/1/20 | Wed 6/3/20 |  | Monir Hossain | Masum Miah
Forcast Approval | 1.2 days | Mon 6/1/20 | Tue 6/2/20 |  | Julhas Razu | Masum Miah
P.O From Multiple Requisition | 2.2 days | Mon 6/3/20 | Wed 6/6/20 |  | Nadia Rashid | Saiful Islam
Party Code Change Against Purchase | 1.2 days | Wed 6/3/20 | Thu 6/4/20 | 38 | Monir Hossain | Masum Miah
Stock Management
Campaign Material Requisition | 2 days | Tue 6/2/20 | Thu 6/4/20 | 37 | Mukul Ahmed | Masum Miah, Saiful Islam, Ashikur ul alam
Campaign Stock Return | 2.2 days | Thu 6/4/20 | Mon 6/8/20 |  | Monir Hossain | Saiful Islam, Masum Miah
Physical Inventory | 1 day | Wed 6/6/20 | Thu 6/7/20 | 40 | Nadia Rashid | Masum Miah
Inventory Adjustment | 2.2 days | Tue 6/2/20 | Thu 6/4/20 | 39 | Julhas Razu | Ashikur ul alam
Cost Finilization (PO) | 2 days | Mon 6/8/20 | Tue 6/9/20 |  | Monir Hossain | Ashikur ul alam, Saiful Islam
Reconcilation | 2 days | Thu 6/4/20 | Mon 6/8/20 | 43 | Mukul Ahmed | Saiful Islam
Sales
Sales Man Target | 1.1 days | Thu 6/4/20 | Sun 6/7/20 | 46 | Julhas Razu | Ashikur ul alam
Sales Return | 1 day | Thu 6/7/20 | Sun 6/9/20 | 45 | Nadia Rashid | Ashikur ul alam
Warehouse wise target setup | 1 day | Tue 6/9/20 | Tue 6/9/20 | 48 | Mukul Ahmed | Ashikur ul alam
Salesman changes from offer/invoice | 1.1 days | Sun 6/7/20 | Mon 6/8/20 | 50 | Julhas Razu | Ashikur ul alam
Service Management | 1 day? | Thu 5/14/20 | Thu 5/14/20
Back process in every step | 1 day | Thu 5/14/20 | Thu 5/14/20
Unpost Service GL | 1 day? | Thu 5/14/20 | Thu 5/14/20
Customer Satisfaction Index | 1 day? | Thu 5/14/20 | Thu 5/14/20
Delivery For Cancel Estimation | 1 day? | Thu 5/14/20 | Thu 5/14/20
Warehouse wise service target Setup | 1 day? | Thu 5/14/20 | Thu 5/14/20
Principle Warranty Claim | 1 day? | Thu 5/14/20 | Thu 5/14/20
Financial Accounting | 5.5 days | Thu 5/14/20 | Thu 5/21/20
Adjust Paid Entry With Accounts | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Advance Adjustment Payable | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Adjust Received Entry With Accounts | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Advance Adjustment Receivable | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Mis Report Setup | 1 day | Thu 5/14/20 | Thu 5/14/20
MIS REPORTING Setup | 1 day | Thu 5/14/20 | Thu 5/14/20
Receivable Top Sheet Preparation | 1 day | Thu 5/14/20 | Thu 5/14/20
Pre Journal Voucher | 1 day | Thu 5/14/20 | Thu 5/14/20
Unpost Transactions | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Opening Balance Entry | 1 day | Thu 5/14/20 | Thu 5/14/20
Cheque Prininting | 4 hrs | Thu 5/14/20 | Thu 5/14/20
Pre Payment Voucher | 1 day | Thu 5/14/20 | Thu 5/14/20
Post Dated Cheque Receiva | 1 day | Thu 5/14/20 | Thu 5/14/20
Bank Reconciliation | 1 day | Thu 5/14/20 | Thu 5/14/20
Year Closing | 1 day | Thu 5/14/20 | Thu 5/14/20
Item Wise New rate upload(Excel Facility) | 2 days | Tue 5/19/20 | Thu 5/21/20 | 21